{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["My To Do EPCO","Légende"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"My To Do EPCO","index":0,"n_rows":15,"n_cols":14,"rows_kept":15,"cut":false,"hidden":false,"merged":[[2,2,2,4]]}
["My to do List",null,"Nom:",null,"Emna ben Mahmoud",null,null,null,null,null,null,null,"Date mise à jour:","2020-09-14"]
[]
["N°","Priority","Responsible/Subject /Task (s)",null,null,"Actual action details/output","Statut","Deadline actual action","Deadline task","Start date","Last update","Date fin","% avancement","Comment"]
[1,"Hight","Accountant ","Internal","Financial Statements 2018/2019/2020:\nBalance sheet\nIncome statement\nCash flow statement.","Review and finalization financial statement 2018/2019 and 2020","In progress","2021-04-23","2021-04-23","-","2021-04-16",null,null,"“Impôt sur les sociétés” will increase within 4 years to the maximum of 25%.\nThis means that for 2018 is 0% (Rachid told us that he will speak with the ministry to accept 0% for 2018 despite the founding in 2017 as in this year no business was ongoing.\n2019 must be in the logical row 8,25%, 2020 with 16,5% and in 2021 with 25%.\n"]
[null,null,"Emna","Internal","EPCO's offshore establishment"]
[2,"Low","EPCO","Internal","Development of Business Plan EPCO Consulting ","Develop the turnover expected in 2021-2022 based on assumptions","In progress","2020-09-18","2020-10-15","2020-08-23","2020-09-14"]
[3,"Low","EPCO","Internal","Development of internal costs",null,"In progress"]
[7,"Hight","EPCO/ANME","Internal","ANME Certificate","Folder preparation","Started","-","-","2020-06-01"]
[null,"Hight","Emna","Internal","New office ","Collect prices and selection of best offers","In progress"]
[]
[null,null,"Development","External","MV projects service prices"]
[4,"Urgent","Sales","External","Price offer Global evolution",null,"In progress"]
[5,"Low","Sales","External","Price offer alliance group",null,"Done","-","-","-"]
[null,null,"Sales","External","Price offer for POULINA group"]
[null,null,null,"External","Price offer Parenin: trainings"]

{"sheet":"Légende","index":1,"n_rows":11,"n_cols":4,"rows_kept":11,"cut":false,"hidden":false,"merged":[]}
[null,null,"priority","status"]
[]
[null,1,"Critical","open"]
[]
[null,2,"Urgent","Started"]
[]
[null,3,"Hight","In progress"]
[]
[null,4,"Medium","Done"]
[]
[null,5,"Low","Deleted"]